## Sheet1
Week | <component> | Severity | Team | Story Points | Components
20/08/2022 | Create spreadsheet of project plan | Easy | DevOps | 1 | Infrastructure
| Create trello board | Easy | DevOps | 1 | Infrastructure
| Create GitHub repo | Easy | DevOps | 1 | Infrastructure
| Create ssh-keys and upload these keys to your GitHub | Easy | DevOps | 1 | Infrastructure | How to Estimate Story Points in Agile?
21/08/2022 | Create Makefile | Medium | DevOps | 2 | Infrastructure | In most cases a story point uses one of the following scales for sizing:
| Create reuirements.txt | Medium | DevOps | 2 | Infrastructure
| Create a python virtual environment | Medium | DevOps | 2 | Infrastructure | 1,2,4,8,16
| Run make all Command and Ensure all tests passed | Medium | DevOps | 2 | Infrastructure | X-Small, Small, Medium, Large, Extra-Large ( known as “T-Shirt Sizing”)
22/08/2021 | Get Scaffolding Code | Easy | DevOps | 1 | Infrastructure | Fibonacci sequence: Series of numbers where each number is the sum of the two previous numbers:1,1,2,3,5,8,13,21
| Ensure the app runs locally without errors | Medium | DevOps | 3 | Infrastructure
| Ensure the app runs in Cloud Shell without errors | Medium | DevOps | 3 | Infrastructure | Here, in we have decided to use Fibonacci sequence, maybe you are wondering why?
23/08/2022 | Set up GitHub Actions | Medium | DevOps | 3 | Infrastructure | Please refer to below link:
| Verify remote tests pass in Github Actions UI | Medium | DevOps | 3 | Infrastructure | Why the Fibonacci Sequence Works Well for Estimating
| Add the GitHub Actions badge to the README | Medium | DevOps | 1 | Infrastructure
24/08/2022 | Replace the scaffolding code with the flask code | Easy | DevOps | 1 | Infrastructure
| Create the App Service in Azure and Authorize it | Easy | DevOps | 2 | Infrastructure
| Enable continous deployment with Azure Pipelines | Medium | DevOps | 5 | Infrastructure
| Enable Github + Azure Pipelines | Difficult | DevOps | 3 | Infrastructure
| Set up the Azure DevOps pipeline | Difficult | DevOps | 5 | Infrastructure
| Verify Prediction with Starter Code locally and remotely | Difficult | DevOps | 2 | Infrastructure
25/08/20212 | Create architectural diagram | Easy | DevOps | 1 | Infrastructure
| Take screenshots demonstrating key steps | Easy | DevOps | 1 | Infrastructure
| Create README file with full instructions of how to run the code | Easy | DevOps | 3 | Infrastructure
| Create demo video and post to YouTube | Easy | DevOps | 3 | Infrastructure
Goals
Building a CI/CD Pipeline
Q4 plan | Introduce Sonarcube and Selenium Tests
Yearly plan | Review the code and ensure it still works