## Sheet1
Quarterly plan | 2021 Q2 |  | ML application - MVP
Week | Backend |  | CI/CD |  | Quality
2021-04-01
2021-04-08 | Setup project (Repo, Readme, Skeleton) | S |  |  | Start documentation | S
2021-04-15 | Implement API as Flask app | M
2021-04-22 | Implement API tests | S |  |  | Validate API tests locally | S
2021-04-29 |  |  | Setup CI Build Server (GitHub Actions) | S | Validate CI process | S
2021-05-06 | Implement core functions using SciKit | M
2021-05-13 | Implement unit tests for core functions | S |  |  | Validate unit tests locally | S
2021-05-20 |  |  | Setup Cloud-native CI/CD (Azure Pipeline) | S | Validate delivery process | S
2021-05-27 | Implement load test | M
2021-06-03 |  |  | Add load test result as quality gate | S | Validate load KPIs | S
2021-06-10 | Backend ready for QA |  | CI/CD ready for QA |  | QA | M
2021-06-17 |  |  |  |  | QA | M
2021-06-24 |  |  |  |  | QA | M
| Goals |  | Goals |  | Goals
| API available | Effort (S,M,L) | Integration automated | Effort (S,M,L) | Tests passed | Effort (S,M,L)
| ML functionality integrated |  | Delivery automated |  | Valid quality gates esists
| Logging in place |  | Deployed on Azure